## Werkblad 2 - Sprint Plan #2 Gam
Sprint Plan #2 group 4 - Virtual Humans for serious gaming
User Story | Task | Task Assigned To | Task completed by | priority (1>2>3) | Estimated Effort per Task | Actual Effort per Task (in Hours) | Done (yes/no) | Notes
| Emergent architecture design |  |  | 1 | 4
| Contact agent and bridge group about relevant percepts | Yannick |  | 2 | 2
| Contact other groups about evaluation triggers | Yannick |  | 3 | 2
| Client meeting | Yannick |  | 1 | 1.5
| Think about git pull requests | Yannick |  | 2 | 1
Understand GOAL | GOAL setup | Everybody |  | 1 | 8
| Understanding GOAL architecture | Joost |  | 1 | 10
| Analyse where the emotion evalutation should be in GOAL |  |  | 2 | 8
| Place first emotion predicate in GOAL |  |  | 3 | 8
GAM java port | Contact group 3 (GAM plugin) about GAM and GOAL | Yannick |  | 1 | 4
| Understanding GAM java port |  |  | 1 | 4
[5 empty] | 52.5 | 0 |  | This week there were only 2 project blocks where we could work on the actual project.
*GAM = gamygdala