## Werkblad 2 - Sprint Plan #2 Gam
Sprint Plan #2 group 4 - Virtual Humans for serious gaming
User Story | Task | Task Assigned To | priority (1>2>3) | Estimated Effort per Task | Notes
| Emergent architecture design | Max | 1 | 4
| Contact agent and bridge group about relevant percepts | Yannick | 2 | 2
| Contact other groups about evaluation triggers | Yannick | 3 | 2
| Client meeting | Yannick | 1 | 1.5
| Think about git pull requests | Yannick | 2 | 1
| Maven en dergelijke opzetten | Everybody | 1 | 4 | With TravisCI, Octopull
Understand GOAL | GOAL setup | Everybody | 1 | 8
| Understanding GOAL architecture | Joost | 1 | 10
| Analyse where the emotion evalutation should be in GOAL | Bernd | 2 | 8
| Place first emotion predicate in GOAL | Rolf | 3 | 8
GAM java port | Contact group 4 (GAM plugin) about GAM and GOAL | Yannick | 1 | 4
| Understanding GAM java port | Max | 1 | 4
|  |  |  | 56.5 | This week there are only 2 project blocks where we can work on the actual project.
*GAM = gamygdala