## Werkblad 1 - Sprint Plan #1 Gam
Sprint Plan #1 group 4 - Virtual Humans for serious gaming
User Story | Task | Task Assigned To | priority (1>2>3) | Estimated Effort per Task | Notes
User is able to play a simple game | find out how phaser works and how to implement a game | Max | 1 | 5 | every body needs to do this, hence the hours
| looking into basic games "Joost" | Joost | 2 | 5 | again everybody needs to know how they work
| come up with game concept | Rolf - Yannick | 1 | 3
| implementing the core game | Bernd (working with Rolf) | 1 | 20 | everybody will work on it, Bernd is responsible
| implementing second game | Joost (Working with Max) | 3 | 15
User is able to play a simple game which involes emotions | finding out how GAM works (checking code + documentation) and summarize | Rolf | 1 | 4
| game mechanics integration with GAM | Yannick | 1 | 15 | We did this by implementing a first and second game
| finding out how to communicate with GAM | Max (working with Bernd) | 1 | 5 | We did this by implementing a first and second game
|  |  |  | 72 | NOTE: This week we will probably all work out how these software implementations work so we weren't able to decice very specifically what we will do.
| *GAM = gamygdala |  |  | This is a first indication. When people finished their tasks, they can help others to match the effort.