## Werkblad 1 - Sprint Plan #1 Gam
Sprint Plan #1 group 4 - Virtual Humans for serious gaming
User Story | Task | Task Assigned To | Task completed by | priority (1>2>3) | Estimated Effort per Task | Actual Effort per Task (in Hours) | Done (yes/no) | Notes
User is able to play a simple game | find out how phaser works and how to implement a game | Max | Everybody | 1 | 5 | 4 | yes | every body needs to do this, hence the hours
| looking into basic games "Joost" | Joost | Everybody | 2 | 5 | 2 | yes | again everybody needs to know how they work
| come up with game concept | Rolf - Yannick | Everybody | 1 | 3 | 1 | yes
| implementing the core game | Bernd (working with Rolf) | Max and Bernd | 1 | 20 | 20 | yes | everybody will work on it, Bernd is responsible
| implementing second game | Joost (Working with Max) | Joost and Yannick | 3 | 15 | 15 | yes
User is able to play a simple game which involes emotions | finding out how GAM works (checking code + documentation) and summarize | Rolf | Everybody | 1 | 4 | 2 | yes
| game mechanics integration with GAM | Yannick | Noone | 1 | 15 | 0 | yes | We did this by implementing a first and second game
| finding out how to communicate with GAM | Max (working with Bernd) | Noone | 1 | 5 | 0 | yes | We did this by implementing a first and second game
| Product vision document |  | Rolf | 1 | 0 | 12 | yes | We did not anticipate having to write a report
| Client meeting |  | Yannick | 1 | 0 | 1.5 | yes
[5 empty] | 72 | 57.5 |  | NOTE: This week we will probably all work out how these software implementations work so we weren't able to decice very specifically what we will do. This week we only had 2,5 project blocks where we could actually work on the project, the other blocks were occupied with a free day or classes.
| *GAM = gamygdala |  |  |  | This is a first indication. When people finished their tasks, they can help others to match the effort.